## Slide 1
  1- Revamping of Holy Family Hospital Rawalpindi.
Scope
RENOVATION / REVAMPING OF BLOCK “A”(Old Block).
Basement Portion, Ground Floor (Left Side) Portion /Remaining Portion) First Floor (Left Side Portion / Remaining Portion) Second Floor Roof Treatment of Block & Storm Drain i/c 5% PST of Block-A(Total Area to be revamped=140377 S.ft).
RENOVATION / REVAMPING OF BLOCK “B” (New Block).
2. (Basement Portion (Complete) Ground Floor (Complete) & First Floor(Complete) Second Floor(Complete) & Roof Treatment & Façade of Block-B) Block-A (Total area to be revamped=465411 Sft)
Project Brief
Sponsoring Agency SHC&MED
Executing Agency C&WD
Approval Date Original .14.10.2023.
Revised. 22.01.2024.
Approved Cost Original .Rs.1546.878 (M)
Revised. Rs.3024.939 (M).
Expenditure upto June 24 3022.760 (M)
Releases 3022.760 (M)
Contractor Old Block: M/S Ali & Brother
New Block: M/S Uni Builders
Resident Supervision M/S AZE Consulting Engineers
Progress
Planned Progress 98%
Physical Progress 98%
Financial Progress 100%
Implementation Status
Date of Start 22.10.2023
Actual Date of Start after vacation
Targeted Date of Completion 30.06.2024.
Expected Date of Completion 30-06-2024
As desired by CM Punjab
Revised Rough cost estimate Rs. 3607.819 Million sent to The Secretary Specialized Healthcare & Medical education on dated 24-05-2024 for arranging revised AA.